## Instructions
		Using the Status tracker

At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
	If 5 team members each spent an hour, that counts as 5 hours
	Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)

For new activities, identify the type of activity - documentation, coordination, estimation etc.

At the end of each week, plan ahead for the following week
	Identify people responsible for each activity
	Estimate the hours needed for the activity

TEAM NAME	SSAD TEAM22(Abhuyday)
PROJECT NAME	Students World
PROJECT MENTOR	Piyush Jain
TEAM MEMBERS	Satyam Pandey
	Animesh Chandra Pathak
	R.V Sahiti
	Pratyusha Musunuru

## Team_Status
TEAM NAME	SSAD TEAM22(Abhuyday)
PROJECT NAME	Students World
PROJECT MENTOR	Piyush Jain

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %
Week 5 (August 31- sept 6)
Learn Eclipse	Preparation	Pratyusha	16	18.5	Ongoing	Using IDEs can make our job easier	-2.5	13.5135135135
Role preferences	Coordination	R.V Sahithi	1	1	Done		0	0
Andriod Studio setup	Preparation	Animesh	20	29	Done		-9	31.0344827586
Develop questions for requirements elicitation	Documentation	Satyam	4	4	Planned	Make sure scoping questions are included	0	0
Research existing technology	Preparation	R.V Sahithi	4	8	Ongoing		-4	50
Project synopsis writeup	Documentation	Satyam	2	2	Planned		0	0
Team Meeting	Coordination	Animesh	2	4	Done		-2	50
Status tracker	Documentation	Pratyusha	2	2	Done		0	0

Week 6 (sept 7- sept 13)
SRS Creations	Documentation	Satyam	8	9.5	Done		-1.5	15.7894736842
Learn Java	Preparation	R.V Sahithi	10	13.5	Ongoing		-3.5	25.9259259259
Configure Tomcat	Preparation	Pratyusha	7.5	6	Done		1.5	25
Learn Andriod Studios	Preparation	Animesh	12.5	12	Ongoing		0.5	4.1666666667
Status tracker	Documentation	Satyam	1	1	Done		0	0
Team Meeting	Coordination	Pratyusha	8	8	Done		0	0

Week 7 (sept 14 - sept 20)
Create Javaservlet	Development	Satyam	13	13	Ongoing		0	0
Create Login,Register	Development	Animesh	7.5	6.5	Done		1	15.3846153846
Create Edit Profile	Development	R.V Sahithi	12	14.5	Done
Create Test	Development	Pratyusha	16	18	Ongoing		0.25	0.25
Stastus Tracker	Documentation	Pratyusha	1	1	Done		0	0
Team Meeting	Coordination	Satyam	4	4	Done		0	0

Week 10

Week 11

Week 12

Week 13

Week 14

Week 15

Week 16

Week 17

## Individual_Status
TEAM NAME	Abhyuday
PROJECT NAME	StudentWorld
PROJECT MENTOR	Piyush Jain,Wisdom Kites

Actvities	SAHITHI R V		PRATYUSHA MUSUNURU		ANIMESH PATHAK		SATYAM PANDEY		Estimated Total Hours	Actual Total Hours
	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent
Week 5 (August 31- sept 6)
Learn Eclipse	4	5	4	5	4	4.5	4	4	16	18.5
Role preferences	0.25	0.25	0.25	0.25	0.25	0.25	0.25	0.25	1	1
Requirements elicitation	1	1	1	1	1	1	1	1	4	4
Andriod Studio setup	5	10	5	7	5	6	5	6	20	29
Research existing technology	1	2	1	2	1	2	1	2	4	8
Project synopsis writeup	0.5	0.5	0.5	0.5	0.5	0.5	0.5	0.5	2	2
Team Meeting	0.5	1	0.5	1	0.5	1	0.5	1	2	4
Status tracker	0.5	0.5	0.5	0.5	0.5	0.5	0.5	0.5	2	2

Week 6 (sept 7- sept 13)
SRS Creations	2	2.5	2	2	2	2.5	2	2.5	8	9.5
Learn Java	3	4	3	4	2	3	2	2.5	10	13.5
Configure Tomcat	2	1.5	2	2	2	1.5	1.5	1	7.5	6
Learn Andriod Studios	2.5	3	3	3	4	3	3	3	12.5	12
Status tracker	0	0	0.5	0.5	0	0	0.5	0.5	1	1
Team Meeting	2	2	2	2	2	2	2	2	8	8

Week 7 (sept 14 - sept 20)
Create Javaservlet	4	3	3	4	3	3	3	3	13	13
Create Login,Register	3	2	2	2	1	1.5	1.5	1	7.5	6.5
Create Edit Profile	3	4	3	4	3	3	3	3.5	12	14.5
Create Test	3	4	4	4.5	4	5	5	4.5	16	18
Stastus Tracker	0	0	0.5	0.5	0	0	0.5	0.5	1	1
Team Meeting	1	1	1	1	1	1	1	1	4	4