## Instructions
		Using the Status tracker

At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
	If 5 team members each spent an hour, that counts as 5 hours
	Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)

For new activities, identify the type of activity - documentation, coordination, estimation etc.

At the end of each week, plan ahead for the following week
	Identify people responsible for each activity
	Estimate the hours needed for the activity

TEAM NAME	SSAD TEAM22(Abhuyday)
PROJECT NAME	Students World
PROJECT MENTOR	Piyush Jain
TEAM MEMBERS	Satyam Pandey
	Animesh Chandra Pathak
	R.V Sahiti
	Pratyusha Musunuru

## Team_Status
TEAM NAME	SSAD TEAM22(Abhuyday)
PROJECT NAME	Students World
PROJECT MENTOR	Piyush Jain

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %
Week 5 (August 31- sept 6)
Learn Eclipse	Preparation	Pratyusha	16	18.5	Ongoing	Using IDEs can make our job easier	-2.5	13.5135135135
Role preferences	Coordination	R.V Sahithi	1	1	Done		0	0
Andriod Studio setup	Preparation	Animesh	20	29	Done		-9	31.0344827586
Develop questions for requirements elicitation	Documentation	Satyam	4	4	Planned	Make sure scoping questions are included	0	0
Research existing technology	Preparation	R.V Sahithi	4	8	Ongoing		-4	50
Project synopsis writeup	Documentation	Satyam	2	2	Planned		0	0
Team Meeting	Coordination	Animesh	2	4	Done		-2	50
Status tracker	Documentation	Pratyusha	2	2	Done		0	0

Week 6 (sept 7- sept 13)
SRS Creations	Documentation	Satyam	8	9.5	Done		-1.5	15.7894736842
Learn Java	Preparation	R.V Sahithi	10	13.5	Ongoing		-3.5	25.9259259259
Configure Tomcat	Preparation	Pratyusha	7.5	6	Done		1.5	25
Learn Andriod Studios	Preparation	Animesh	12.5	12	Ongoing		0.5	4.1666666667
Status tracker	Documentation	Satyam	1	1	Done		0	0
Team Meeting	Coordination	Pratyusha	8	8	Done		0	0

Week 7 (sept 14 - sept 20)
Create Javaservlet	Development	Satyam	13	13	Ongoing		0	0
Create Login,Register	Development	Animesh	7.5	6.5	Done		1	15.3846153846
Create Edit Profile	Development	R.V Sahithi	12	14.5	Done
Create Test	Development	Pratyusha	16	18	Ongoing		0.25	0.25
Status tracker	Documentation	Pratyusha	1	1	Done		0	0
Team Meeting	Coordination	Satyam	4	4	Done		0	0

Week 8 (sept 21 - sept 28)
Otp Activity	Development	Animesh	10	11	Done
MYSQL database	Development	Satyam	7	7	Ongoing
Connectiong Client to Server	Development	R.V Sahithi	11	11	Done
Status tracker	Documentation	Pratyusha	0.5	0.5	Done
Team Meeting	Coordination	Pratyusha	4	4	Done

Week 9 (sept 29 – Oct 6)
Presentation	Documentation	Pratyusha	8	8	Done
Test Backend	Development	Satyam	3	4	ongoing
Screen Cast	Documentation	Animesh	4	4	done
Status tracker	Documentation	Pratyusha	0.5	0.5	done
Team Meeting	Coordination	R.V Sahithi	8	8	done

Week 10(Oct 26 – Nov 3 )
Create Post Backend	Development	R.V Sahithi	3	4	done		-1	25
Create Post Frontend	Development	Pratyusha	3	4	ongoing
Test Frontend	Development	Animesh	8	9	ongoing
Test Backend	Development	Satyam	6	7	done
Status tracker	Documentation	Pratyusha	0.5	0.5	done
Team Meeting	Coordination	Animesh	2	2	done		0	0

Week 11(Nov 4 – Nov 11)
Embed Templates	Development	R.V Sahithi	5	6	ongoing		-1	16.6666666667
Comment Frontend	Development	Pratyusha	2	3	ongoing
Comment Backend	Development	R.V Sahithi	2	3	Done
Status tracker	Documentation	Pratyusha	0.5	0.5	Done
Team Meeting	Coordination	Satyam	2	2	Done
Test Plan	Documentation	Animesh	1	1	Ongoing		0	0

Week 12(Nov 12 – Nov 19)
Tabbed Activity	Development	Pratyusha	2	2	Done		0	0
Test Evaluation	Development	Satyam	9	12	Done		-3	25
Team Meeting	Coordination	Satyam	8	8	Done		0	0
View Post	Coordination	R.V Sahithi	6	7	Done
Status tracker	Documentation	Pratyusha	0.5	0.5	Done		0	0
Side Pane	Development	R.V Sahithi	6	6	Done
Question Activity	Development	Animesh	7	10	Done
Topic Activity	Development	Animesh	8	11	Done

Week 13(Nov 20 -Nov 24)
Presentation	Documentation	Animesh	8	8	Ongoing		0	0
Status tracker	Documentation	Pratyusha	0.5	0.5	Done		0	0
Submit Everything	Documentation	R.V Sahithi	8	8	Ongoing

Week 14

Week 15

Week 16

Week 17

## Individual_Status
TEAM NAME	Abhyuday
PROJECT NAME	StudentWorld
PROJECT MENTOR	Piyush Jain,Wisdom Kites

Actvities	SAHITHI R V		PRATYUSHA MUSUNURU		ANIMESH PATHAK		SATYAM PANDEY		Estimated Total Hours	Actual Total Hours
	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent
Week 5 (August 31- sept 6)
Learn Eclipse	4	5	4	5	4	4.5	4	4	16	18.5
Role preferences	0.25	0.25	0.25	0.25	0.25	0.25	0.25	0.25	1	1
Requirements elicitation	1	1	1	1	1	1	1	1	4	4
Andriod Studio setup	5	10	5	7	5	6	5	6	20	29
Research existing technology	1	2	1	2	1	2	1	2	4	8
Project synopsis writeup	0.5	0.5	0.5	0.5	0.5	0.5	0.5	0.5	2	2
Team Meeting	0.5	1	0.5	1	0.5	1	0.5	1	2	4
Status tracker	0.5	0.5	0.5	0.5	0.5	0.5	0.5	0.5	2	2

Week 6 (sept 7- sept 13)
SRS Creations	2	2.5	2	2	2	2.5	2	2.5	8	9.5
Learn Java	3	4	3	4	2	3	2	2.5	10	13.5
Configure Tomcat	2	1.5	2	2	2	1.5	1.5	1	7.5	6
Learn Andriod Studios	2.5	3	3	3	4	3	3	3	12.5	12
Status tracker	0	0	0.5	0.5	0	0	0.5	0.5	1	1
Team Meeting	2	2	2	2	2	2	2	2	8	8

Week 7 (sept 14 - sept 20)
Create Javaservlet	4	3	3	4	3	3	3	3	13	13
Create Login,Register	3	2	2	2	1	1.5	1.5	1	7.5	6.5
Create Edit Profile	3	4	3	4	3	3	3	3.5	12	14.5
Create Test	3	4	4	4.5	4	5	5	4.5	16	18
Status Tracker	0	0	0.5	0.5	0	0	0.5	0.5	1	1
Team Meeting	1	1	1	1	1	1	1	1	4	4

Week 8(Sept 21 – Sept 28)
Otp Activity	3	4	2	2	3	3	2	2	10	11
Mysql Database	1	1	2	2	2	2	2	2	7	7
Connecting Client and Server	2	2	3	3	3	3	3	3	11	11
Status Tracker	0	0	0.5	0.5	0	0	0	0	0.5	0.5
Team Meeting	1	1	1	1	1	1	1	1	4	4

Week 9(Sept 29 – Oct 6)
Presentation	2	2	2	2	2	2	2	2	8	8
Test Backend	0	0	0	0	0	0	3	4	3	4
Screen Cast	0	0	0	0	2	2	2	2	4	4
Status Tracker	0	0	0.5	0.5	0	0	0	0	0.5	0.5
Team Meeting	2	2	2	2	2	2	2	2	8	8

Week 10(Oct 26 – Nov 3)
Create Post Frontend	0	0	3	4	0	0	0	0	3	4
Create Post Backend	3	4	0	0	0	0	0	0	3	4
Test Frontend	2	2	3	3	3	4	0	0	8	9
Test Backend	2	3	0	0	0	0	4	4	6	7
Status Tracker	0	0	0.5	0.5	0	0	0	0	0.5	0.5
Team Meeting	0.5	0.5	0.5	0.5	0.5	0.5	0.5	0.5	2	2

Week 11(Nov 4 – Nov 11)
Embed Templates	5	6	0	0	0	0	0	0	5	6
Comment Backend	2	3	0	0	0	0	0	0	2	3
Comment Frontend	0	0	2	3	0	0	0	0	2	3
Status Tracker	0	0	0.5	0.5	0	0	0	0	0.5	0.5
Team Meeting	0.5	0.5	0.5	0.5	0.5	0.5	0.5	0.5	2	2
Test Plan	0.5	0.5	0.5	0.5	0	0	0	0	1	1

Week 11(Nov 12 – Nov 20)
Tabbed Activity	1	1	1	1	0	0	0	0	2	2
Test Evaluation	2	3	0	0	3	4	4	5	9	12
Team Meeting	2	2	2	2	2	2	2	2	8	8
View Post	3	3	2	3	0	0	1	1	6	7
Status tracker	0	0	0.5	0.5	0	0	0	0	0.5	0.5
Side Pane	3	3	3	3	0	0	0	0	6	6
Question Activity	2	3	0	0	3	4	2	3	7	10
Topic Activity	3	4	0	0	2	3	3	4	8	11

Week 11(Nov 20 – Nov 24)
Presentation	2	2	2	2	2	2	2	2	8	8
Status tracker	0	0	0.5	0.5	0	0	0	0	0.5	0.5
Submit Everything	2	2	2	2	2	2	2	2	8	8